## ACA
Product Readiness Checklist
Application: | Access Content Anywhere (ACA)
Application Stakeholder: | Kristy Litchford
Date Reported: | 2017-11-21
Production Standard | Application Deliverables | App Team Owner | Deliverable Description | Identified Gaps | Action to Remediate | Target PI Remediate Gaps
Security Assessment | Authorization to Operate (ATO) | App Team Product Owner | ACA ATO Document | None
Service Management | Partnership Agreement | App Team Product Owner | ACA Partnership Agreement | None
Availablility Management | Planned Maintenance Window Definition (provide information from App Team's Partnership Agreement here for single place of reference) | App Team Product Owner | Window Group 2 | None | Would like to pursue Window 4 (24 x 7)
Availablility Management | App Team Defined Support Commitment (provide information from App Team's Partnership Agreement here for single place of reference) | App Team Product Owner | Monday - Friday: 8 AM to 5 PM | None
Asset and Inventory Management | Record of existing CI (config items) to be related in Change / Incident / Problem Mgmt process | App Team Operations Resource | No downstream Configuration Items have been defined for ACA under the parent "Azure Cloud Platform" Configuration Item | ACA Configuration Items need to be added to UCMDB and linked as downstream items to CI "Azure Cloud Platform" | http://community.nml.com/sites/itoi/cm/_layouts/15/start.aspx#/SitePages/Home.aspx
Asset and Inventory Management | List of Application and Infrastructure Instances adhere to the prescrbed Azure Foundations resource naming standards | App Team Operations Resource | Resource names adhere to standard. | None
Incident and Problem Management | Definition of Operations contacts and escalation contacts in App Team (provide information from App Team's Partnership Agreement here for single place of reference) | App Team Operations Resource | Elizabeth Kegel Tony Lauf Michele Ottaway | None
Change Mgmt Process | Integration into Standard NM Change Mgmt process for all changes with customer impact | App Team Operations Resource | Follow standard NM change management process for Production
Knowledge Management | Document repository for consumption by Azure Team and App Team (Internal audience) | App Team Documentation Resource | ACA Internal Sharepoint
Knowledge Management | Document repository for consumption by Customer / Public (External audience) | App Team Documentation Resource | {EXTERNAL LINK TO RESOURCE} Team's sharepoint site used for External Documentation | Future plans to use Swagger for self-documenting code | Need to create collateral for other dev groups
Build and Deployment | No restriction in Lab (automation is not required) | App Team DevOps Resource | Not currently used
Build and Deployment | Automated delivery in Test Env (Example via Ansible/CICD/Integrated Testing) | App Team DevOps Resource | Infra could be recreated from playbooks, but some Nuxeo admin work (like user group creation) is manual after the fact, manually pull down Nuxeo ACA configuration from Nuxeo Market place, Ansible app playbooks deploy the code to the environments - No test Tower exists, laptop has to act as Tower | Manual Nuxeo Admin configuration work, manual pull of Nuxeo ACA config from Market place, no 'test' tower available
Build and Deployment | Automated delivery in Stage Env (Example via Ansible/CICD/Integrated Testing) | App Team DevOps Resource | Infra could be recreated from playbooks, but some Nuxeo admin work (like user group creation) is manual after the fact, manually pull down Nuxeo ACA configuration from Nuxeo Market place, Ansible app playbooks deploy the code to the environments - Using Stage Tower | Manual Nuxeo Admin configuration work, manual pull of Nuxeo ACA config from Market place, no 'stage' tower available
Build and Deployment | Automated delivery in Prod Env (Example via Ansible/CICD/Integrated Testing) | App Team DevOps Resource | Infra could be recreated from playbooks, but some Nuxeo admin work (like user group creation) is manual after the fact, manually pull down Nuxeo ACA configuration from Nuxeo Market place, Ansible app playbooks deploy the code to the environments - Using Prod Tower | Manual Nuxeo Admin configuration work, manual pull of Nuxeo ACA config from Market place, no 'prod' tower available
Test Engineering | Unit / Feature testing in Lab / Local Laptop | App Team Quality Assurance Resource | Lab work is done on local laptops with J-Unit for code coverage
Test Engineering | Integration / Regression / Performance / Smoke / Security (Penetration) in Test Env with a Test data set | App Team Quality Assurance Resource | Using team "phoenix" for Integration and performance | Is Phoenix team testing regression? Should an additional security test be implemented?
Test Engineering | Integration / Regression / Performance / Smoke / Security (Penetration) in Stage Env with scrubbed Prod data set | App Team Quality Assurance Resource | IRM completed Penetration testing in Stage | What is ETCC monitoring and where for APM?
Test Engineering | Performance / Smoke / Security (Penetration) in Prod Env with BCP plan to roll back to previous state on failed testing | App Team Quality Assurance Resource | How is 'Prod env' testing completed? {External link to test plan} | What is ETCC monitoring and where for APM? | Ask Manish
Capacity Management | Current architecture considerations for scale | App Team Operations Resource | Vendor input provided for size, quantity, and scale.
Capacity management | Current monitoring thresholds for potential capacity risks (by architectural layers - Web, App, Data) | App Team Operations Resource | Need to document list of resources and points that could be risk for scale. (Memory, disk, CPU, user count, and activity currently noted)
Access Management | Definition of authorization owners and process to gain access to included systems | App Team Security Resource | Customer access is approved by stakeholders on Partnership Agreement, Internal Team access is approved by stakeholders on Partnership Agreement
Access Management | Definition of process to gain access to included systems | App Team Security Resource | iRequest for adding a user to the AD group related to access
Access Management | System accounts and other App related Secrets have established and tested password rotation mechanisms per requirements negotiated between IRM and App team | App Team Security Resource | Assumed that all generic IDs from On-Prem, used in app, are not set to rotate or expire. |  | Manish / Prashanth will provide list to Jeff Rose to check with ESAT
Access Management | "Break Glass" procedures have been established and tested for limited access to Prod resources when allowed by temporary IRM exception | App Team Security Resource | Azure Foundations team ability to provide functionality. Currently tactical. |  | Talk about OMS Custom Log abilities
Event Management | Items within home-office scope | App Team Operations Resource | On-Prem LDAP, CoreD database On-Prem, Audit DBs Client content database, CMOD (ACA team owned), IBM Content Manager |  | Expand on list
Event Management | Monitoring points and defined metrics |  | ACA Monitoring Points | ETCC monitoring
Event Management | Metrics gathering mechanism | App Team Operations Resource | Cloud - Azure Monitor (PaaS), OMS Agent (IaaS) / OnPrem - Tooling? |  | Update for On-Prem (Nick)
Event Management | Monitoring point tresholds defined, notifications created and exercised | App Team Operations Resource | OMS Alerts | Need to be created | Azure Foundations Team to deliver role to instrument monitoring
Event Management | Monitoring treshold response - auto-healing and automation actions | App Team Operations Resource | Email to start |  | dl-aca-support
Event Management | Monitoring point visualizations created and exercised for reporting | App Team Operations Resource | APM for infra Team Center PROD: http://apmprod.nml.com/ApmServer Team Center Stage: http://apmstagenml.com/ApmServer, Netuitive dashboards Netuitive Console PROD: http://npa/sa/elements/service.html?managedElement.id=266205047 NONPROD: http://wss-stna-000695/sa/elements/service.html?managedElement.id=202638793 | OMS Dashboards for infrastructure needed | Azure Foundations Team to Deliver
Event Management | Application Monitoring has been established for key endpoints and resources | App Team Operations Resource | VSM (synthtic transaction) - Redis / ElasticSearch, UIM - Mongo (Greg G's team) - aggregated in Netuitive
Event Management | Security Monitoring has been established for all items defined between App team and Security Teams (IRM + InfraSec) | App Team Operations Resource | Splunk and Qualys have been integrated in VMs - ATO and Pen testing completed
Update Management | Resource lifecycle (30 days or less and recreate, or 30 days or more and require patching) | App Team Operations Resource | No patching established | Need to implement Ansible Patching Role | Azure Foundations Team to partner with ACA to implement
Data Management | Identification of Database or other fixed resources that require backup at a specific cadence to support BCP requirements | App Team Operations Resource | ACA Data Assets
Data Management | Established and exercised backup process for resources identified above | App Team Operations Resource | Process and last time exercised? {{ EXTERNAL }}
Business Continuity Planning | BCP Runbook (Definition of Disaster Recovery procedure - #4) | App Team Product Owner | ACA BCP Runbook
Business Continuity Planning | Planned cadence for exercising DR procedure (#5) | App Team Product Owner | Example: Quarterly, Bi-Annually, etc
Business Continuity Planning | BCP Plan has been exercised successfully once more more before App goes to Prod | App Team Product Owner | {EXTERNAL LINK - BCP Results} Exercised on 10/25/2017 signed off by App Owner XYZ on 10/26/2017
Architecture Management | System architecture and data flow incorporates considerations for redundancy, high availability, disaster DR strategy without any single points of failure | App Team Operations Resource | ACA System Architecture | Need to evaluate with customer

## Sample App Input
Product Readiness Checklist
Application: | Employee Training App
Application Stakeholder: | Sign off ability for whole list
Date Reported: | 2017-11-01
Production Standard | Application Deliverables | App Team Owner | Deliverable Description | Identified Gaps | Target PI Remediate Gaps
Security Assessment | Authorization to Operate (ATO) | App Team Product Owner | {EXTERNAL LINK TO DELIVERABLE} Taken necessary actions to obtain ATO | None
Service Management | Partnership Agreement | App Team Product Owner | {EXTERNAL LINK TO DELIVERABLE} Partnership Agreement established | None
Availablility Management | Planned Maintenance Window Definition (provide information from App Team's Partnership Agreement here for single place of reference) | App Team Product Owner | Availability Window Group 1 (Friday-Monday from 6pm to 4am) | None
Availablility Management | App Team Defined Support Commitment (provide information from App Team's Partnership Agreement here for single place of reference) | App Team Product Owner | 24 x 7 (as noted in Partnership Agreement) | None
Asset and Inventory Management | Record of existing CI (config items) to be related in Change / Incident / Problem Mgmt process | App Team Operations Resource | A few of the resources have been added to HPSM, but not all. | There are remaining items that need to be added in HPSM for this App Team's resources.
Asset and Inventory Management | List of Application and Infrastructure Instances adhere to the prescrbed Azure Foundations resource naming standards | App Team Operations Resource | Custom names were used for some resources, but not all. | Using names that do not conform to the Azure Foundation Team's naming standards cause confusion and potential issues running reports in the future.
Incident and Problem Management | Definition of Operations contacts and escalation contacts in App Team (provide information from App Team's Partnership Agreement here for single place of reference) | App Team Operations Resource | Primary Contact = John Smith (App Team SRE Lead), Escalation Contact = Jane Doe (Product Owner) | None
Change Mgmt Process | Integration into Standard NM Change Mgmt process for all changes with customer impact | App Team Operations Resource | Actively using NM Change Mgmt process for all changes to customer impacting environments (infra, code, and data changes) | None
Knowledge Management | Document repository for consumption by Azure Team and App Team (Internal audience) | App Team Documentation Resource | {EXTERNAL LINK TO RESOURCE} NM Wiki Used for Internal Documentation | None
Knowledge Management | Document repository for consumption by Customer / Public (External audience) | App Team Documentation Resource | {EXTERNAL LINK TO RESOURCE} Team's sharepoint site used for External Documentation | None
Build and Deployment | No restriction in Lab (automation is not required) | App Team DevOps Resource | Developers deploy from Tower, Jenkins, or their local laptops | None
Build and Deployment | Automated delivery in Test Env (Example via Ansible/CICD/Integrated Testing) | App Team DevOps Resource | Developers deploy from Tower, Jenkins, or their local laptops | All deployment into Test and upper environments (including Stage and Prod) must be completed by automated mechanisms for infra, code, and data.
Build and Deployment | Automated delivery in Stage Env (Example via Ansible/CICD/Integrated Testing) | App Team DevOps Resource | Infra-code deploy fully automated with Tower roles/playbooks, and code deploy automated with Jenkins release pipeline including integrated testing with Management approvals included in pipeline | None
Build and Deployment | Automated delivery in Prod Env (Example via Ansible/CICD/Integrated Testing) | App Team DevOps Resource | Infra-code deploy fully automated with Tower roles/playbooks, and code deploy automated with Jenkins release pipeline including integrated testing with Management approvals included in pipeline | None
Build and Deployment | Specific Tools / Tool Location | App Team DevOps Resource | Using centralized Jenkins instance | None
Test Engineering | Unit / Feature testing in Lab | App Team Quality Assurance Resource | Developers test ad-hoc with their own Unit tests for Infra-code, App-code, and Data changes | None
Test Engineering | Integration / Regression / Performance / Smoke / Security (Penetration) in Test Env with a Test data set | App Team Quality Assurance Resource | {EXTERNAL LINK to TEST PLAN} (Test plan to include: Infra roles/playbooks are tested manually. App code has automated integration / regression / performance / and security testing included in build/release pipeline. A "test" data set is used for all "test" environment QA activities.) | App code and data sets are safe, but Infra code should have integrated testing. Ad-hoc manual testing is not sufficient.
Test Engineering | Integration / Regression / Performance / Smoke / Security (Penetration) in Stage Env with scrubbed Prod data set | App Team Quality Assurance Resource | {EXTERNAL LINK to TEST PLAN} (Infra and App code are both tested for integration, performance, and security validation. The data set is an exact copy of production data, which has been scrubbed to remove specific customer information.) | None
Test Engineering | Performance / Smoke / Security (Penetration) in Prod Env with BCP plan to roll back to previous state on failed testing | App Team Quality Assurance Resource | {EXTERNAL LINK to TEST PLAN} (Change management is completed prior to any change into Prod as it will have customer impact. Code is deployed to a pre-prod environment. Infra and App code are both tested for performance and security to ensure it performs adequately. Then the pre-prod and Prod environments are flipped to place the code into production. A smoke test is then performed to ensure no major end-to-end functionality is broken. If any defect is found then BCP plan is enacted for a complete roll back to previous state.) | None
Capacity Management | Current architecture considerations for scale | App Team Operations Resource | Infrastructure is built on Azure PaaS Webapps with auto-scale rules set up. | None
Capacity management | Current monitoring thresholds for potential capacity risks (by architectural layers - Web, App, Data) | App Team Operations Resource | Data Layer: Cosmos DB is used for data storage and metrics are gathered to show number of transactions and alert the App Team Operations contact if there is a need to increase Cosmos DB limits (manually). | Cosmos DB limits are not auto-scaled as a response to a high metric, but rather they are handled manually.
Access Management | Definition of authorization owners and process to gain access to included systems | App Team Security Resource | Application Team operations contacts receive tickets through a standard ticketing system for onboarding new users onto the system with their managers approval. | None
Access Management | Definition of process to gain access to included systems | App Team Security Resource | Submit a ticket through the App Team's sharepoint induction form. | None
Access Management | System accounts and other App related Secrets have established and tested password rotation mechanisms per requirements negotiated between IRM and App team | App Team Security Resource | A 'SPN' is used for integration with Azure AD, which does expire annually. A calendar appointment has been set up with Product Owner and management to ensure this does not expire. | Manual interaction and calendar appointments do not ensure the app's SPN renewal will be handled on time.
Access Management | "Break Glass" procedures have been established and tested for limited access to Prod resources when allowed by temporary IRM exception | App Team Security Resource | All resources are PaaS and therefore do not require any "break glass" procedure or access. | None
Event Management | Items within home-office scope | App Team Operations Resource | DB2 on-prem system is monitored with on-prem tools
Event Management | Monitoring points defined and metrics gathered | App Team Operations Resource | Application Team has applied the Azure Foundations Team monitoring metric gathering roles to all resources (PaaS webapp and Cosmos DB) and connected to App Team Log Analytics Workspace | None
Event Management | Monitoring point tresholds defined, notifications created and exercised | App Team Operations Resource | Application Team has applied the Azure Foundations Team monitoring metric gathering roles to all resources (PaaS webapp and Cosmos DB) and specified required thresholds in role variables. Auto-tickets and emails sent. | None
Event Management | Monitoring treshold response - auto-healing and automation actions | App Team Operations Resource
Event Management | Monitoring point visualizations created and exercised for reporting | App Team Operations Resource | Application Team has created basic visualizations for simple queries based on Azure Foundations Team sample KQL queries on Azure Foundations Team Customer WIKI | None
Event Management | Application Monitoring has been established for key endpoints and resources | App Team Operations Resource | Application Team has created alerts when configuring Monitoring roles for resources | None
Event Management | Security Monitoring has been established for all items defined between App team and Security Teams (IRM + InfraSec) | App Team Operations Resource | Application Team does not have any defined security monitoring at this time. | App team needs to reference IRM and Infrasec to define any required Security information.
Update Management | Resource lifecycle (30 days or less and recreate, or 30 days or more and require patching) | App Team Operations Resource | No IaaS resources are included in project so there is nothing to update. | None
Data Management | Identification of Database or other fixed resources that require backup at a specific cadence to support BCP requirements | App Team Operations Resource | Cosmos DB data is backed up through a scheduled webjob. | None
Data Management | Established and exercised backup process for resources identified above | App Team Operations Resource | Backups are scheduled once a week to meet a recovery time objective of 7 days or less data loss. | None
Business Continuity Planning | BCP Runbook (Definition of Disaster Recovery procedure) | App Team Product Owner | A pre-prod quality environment is created and the Cosmos DB data is restored to show functionality can be recovered during a disaster. | None
Business Continuity Planning | Planned cadence for exercising DR procedure | App Team Product Owner | Once a quarter the BCP runbook will be exercised. | None
Business Continuity Planning | BCP Plan has been exercised successfully once more more before App goes to Prod | App Team Product Owner | {EXTERNAL LINK - BCP Results} Exercised on 10/25/2017 signed off by App Owner XYZ on 10/26/2017
Business Continuity Planning | System architecture and data flow do not contain any single points of failure | App Team Operations Resource | {EXTERNAL LINK - System Architecture}
Business Continuity Planning | Current architecture considerations for redundancy / High Availability / Disaster DR Strategy | App Team Operations Resource | {EXTERNAL LINK - System Architecture}